## Tabelle1
Identified | Prob of occurance | Damage | Mitigation strategy | Person in charge | Risk factor
trouble implementing feature | 80% | 3-7 | read documention/ask for help | Paul & Chris | 2,4-5,6
Hardware breaks (e. g. Raspberry, sensor) | 40% | 1-10 | replacement Hardware | Chris | 0,4-4
bad time manangement | 40% | 8 | detailed planning | Olga | 3.2
bad communication | 30% | 7 | communicate | Olga | 2.1
chosing wrong software tools | 5% | 8 | inform well about software features | Paul | 0.4
Illness of team member (> 1 week) | 5% | 7 | eat apples | all | 0.35
prob * damage