## Tabelle1
Identified | prob of occurance | damage | mitigation strategy | person in charge | Risk factor
trouble implementing feature | 80% | 3-7 | read documention/ask for help | all | 240-560
bad time manangement | 40% | 10 | detailed planning | all | 400
Hardware breaks (e. g. Raspberry, sensor) | 40% | 1-10 | replacement Hardware | all | 40-400
bad communication | 30% | 7 | communicate | all | 210
chosing wrong software tools | 5% | 8 | inform well about software features | all | 40
Illness of team member (> 1 weeks) | 5% | 7 | eat apples | all | 35